## Project Plan
Phase | Duration | Goal | Major Deliverables | Exit Criteria
Phase 1 | Weeks 1-3 | AI Foundation | Project setup, FastAPI, Next.js, PostgreSQL, Ollama, Llama 3.1 8B, ChromaDB, PDF upload, RAG chat | Upload PDF and answer procurement questions
Phase 2 | Weeks 4-6 | Document Intelligence | OCR, metadata extraction, document classification, citations | Accurate document understanding
Phase 3 | Weeks 7-10 | Procurement Core | PR, PO, Supplier, Contracts modules | CRUD + workflows
Phase 4 | Weeks 11-14 | AI Copilots | Procurement copilot, contract Q&A, supplier insights | Task assistance
Phase 5 | Weeks 15-18 | Enterprise | RBAC, audit, APIs, monitoring | Production-ready MVP

## Sprint Plan
Sprint | Duration | Epic | Stories | Deliverables
Sprint 1 | Week 1 | Foundation | Repo, Docker, FastAPI, Next.js, PostgreSQL | Running stack
Sprint 2 | Week 2 | AI Infrastructure | Ollama, embeddings, ChromaDB | Local AI operational
Sprint 3 | Week 3 | RAG MVP | PDF upload, chunking, retrieval, chat UI | Working procurement Q&A
Sprint 4 | Week 4 | Authentication | JWT, users, roles | Secure login
Sprint 5 | Week 5 | Documents | Metadata, versioning | Document management
Sprint 6 | Week 6 | Testing | Unit/integration tests, CI | Stable MVP
Sprint 7 | Weeks 7-8 | Procurement | PR & PO | Core procurement
Sprint 8 | Weeks 9-10 | Suppliers | Supplier & contracts | Supplier management
Sprint 9 | Weeks 11-12 | AI Agents | Procurement assistant | Copilot
Sprint 10 | Weeks 13-14 | Hardening | Performance, security | Beta
Sprint 11 | Weeks 15-16 | Enterprise | Audit, APIs | Enterprise features
Sprint 12 | Weeks 17-18 | Release | Documentation, deployment | v1.0